## Overall
Countries' groups and Work Programme
Group | Tot days for Country Experts | Tot days for National Hubs | Tot | Austria | Belgium | Bulgaria | Croatia | Cyprus | Czechia | Denmark | Estonia | Finland | France | Germany | Greece | Iceland | Ireland | Italy | Latvia | Lithuania | Luxembourg | Malta | Netherlands | Poland | Portugal | Romania | Slovakia | Slovenia | Spain | Sweden | Ukraine
A | 83 | 38 | 121
B | 73 | 28 | 101
C | 62.5 | 28 | 90.5
D | 44.5 | 13 | 57.5
E | 37.5 | 12 | 49.5
F | 83 | 93 | 176
Tasks' timeframe | time axis 2023-03-01 to 2026-12-01
T1.3 - Evaluation and selection of benenficiaries
T2.1 - EUCF beneficiaries onboarding
T2.3 - EUCF beneficiaries IC development support
T2.4.1 - Monitoring of IC development
T2.4.2 - IC Validation
TF2.4.3 IC Implementation monitoring
T3.1 - Setting up and engaging a network of country experts and national hubs
T3.2.1 - National helpdesk
T3.2.2 - Application phase training
T3.3 - National launch events
T3.4 - Monitoring of national support
T3.3.2 - National web presence and mailing
T5.1.1 - Database of investors and relevant stakeholders
TF5.1.3 - IC matchaking activities with investors
TF5.3 Pilot schemes

## Workplan Group A
Workplan Group A
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 4.5 | 4.5
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 3 | 5 | 15
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 2 | 2
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 2 | 2
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 40 | 40
WP3 | T3.3 - National launch events | Participate in national events organised by National hubs and cover technical questions, if any, and present LIFE EUCF Calls. | 3 | 3 | 9
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
83
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.1 - National laungh events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 3 | 4 | 12
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 2 | 6
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 9 | 9
WP5 | TF5.1.3 - IC matchaking activities with investors | Support the LIFE EUCF Team in the organisation of roadshows. Support the LIFE EUCF Team in the organisation of national matchmaking events | 1 | 10 | 10
38

## Workplan Group B
Workplan Group B
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 3.5 | 3.5
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 3 | 4 | 12
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 1.5 | 1.5
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 1.5 | 1.5
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 30 | 30
WP3 | T3.2.2 - Application phase training | Organisation of 1 training session for interested applicants on the technical aspects of the application form, also involving external experts for ad-hoc training | 1 | 5 | 5
WP3 | T3.3 - National launch events | Participate in national events organised by National hubs and cover technical questions, if any, and present LIFE EUCF Calls. | 3 | 3 | 9
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
73
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.1 - National laungh events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 3 | 4 | 12
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 2 | 6
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 9 | 9
28

## Workplan Group C
Workplan Group C
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 2 | 2
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 3 | 3 | 9
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 1 | 1
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 1 | 1
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 20 | 20
WP3 | T3.2.2 - Application phase training | Organisation of training sessions for interested applicants on the technical aspects of the application form, also involving external experts for ad-hoc training | 2 | 5 | 10
WP3 | T3.3 - National launch events | Participate in national events organised by National hubs and cover technical questions, if any, and present LIFE EUCF Calls. | 3 | 3 | 9
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
62.5
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.1 - National laungh events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 3 | 4 | 12
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 2 | 6
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 9 | 9
28

## Workplan Group D
Workplan Group D
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 2 | 2
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 1 | 4 | 4
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 1 | 1
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 1 | 1
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 7 | 7
WP3 | T3.2.2 - Application phase training | Organisation of training sessions for interested applicants on the technical aspects of the application form, also involving external experts for ad-hoc training | 2 | 5 | 10
WP3 | T3.3 - National launch events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 3 | 3 | 9
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
44.5
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 1 | 3
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 9 | 9
13

## Workplan Group E
Workplan Group E
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 2 | 2
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 1 | 3 | 3
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 1 | 1
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 1 | 1
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 5 | 5
WP3 | T3.2.2 - Application phase training | Organisation of training sessions for interested applicants on the technical aspects of the application form, also involving external experts for ad-hoc training | 2 | 4 | 8
WP3 | T3.3 - National launch events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 1 | 7 | 7
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
37.5
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 1 | 3
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 8 | 8
12

## Workplan Group F
Workplan Group F
Country Expert
WP | Task | Description of the action | Unit | Days | Total
WP1 | T1.3 Evaluation and selection of applicants | Support the EUCF evaluators in the qualitative evaluation of applications, if needed | 1 | 4.5 | 4.5
WP2 | T2.1 - LIFE EUCF beneficiaries onboarding | Organisation of online conference call with selected applicants and support LIFE EUCF Core Management Team in the negotiation of the Grant Agreement with selected applicants. | 3 | 0.5 | 1.5
WP2 | T2.3 - LIFE EUCF beneficiaries IC development support | Provide guidance to LIFE EUCF beneficiaries during the IC development phase and support the LIFE EUCF Core Management Team in the organistion of peer-to-peer exchanges and knowledge transfer within beneficiaries and participate in expert training sessions. | 1 | 5.5 | 5.5
WP2 | T2.4.1 - Monitoring of IC development | Support the LIFE EUCF Core Management Team in the monitoring of IC development. | 3 | 5 | 15
WP2 | T2.4.2 - IC Validation | Support the LIFE EUCF Core Management Team in the validation of IC and support the LIFE EUCF beneficiaires in addressing evaluators' comments, if any. | 1 | 2 | 2
WP2 | TF2.4.3 IC Implementation monitoring | Support the LIFE EUCF Core Management Team in the monitoring of IC implementation. | 1 | 2 | 2
WP3 | T3.1 - Setting up and engaging a network of country experts and national hubs | Participation in trainings for country experts | 1 | 2.5 | 2.5
WP3 | T3.2.1 - National helpdesk | Provide helpdesk to interested applicants in national language | 1 | 40 | 40
WP3 | T3.3 - National launch events | Participate in national events organised by National hubs and cover technical questions, if any, and present LIFE EUCF Calls. | 3 | 3 | 9
WP3 | T3.4 - Monitoring of national support | Provide timely feedback and monitoring reports | 1 | 1 | 1
83
National Hub
WP | Task |  | Unit | Days | Total
WP3 | T3.3.1 - National laungh events | Organise a launch webinar per each call, including peer-to-peer session, and mobilise potential applicants | 3 | 4 | 12
WP3 | T3.3.2 - National web presence and mailing | Ensure web presence to the LIFE EUCF in th emain channels in the country. Translate and adapt press releases, dedicate emails and LIFE EUCF announcements and social media presence. Support synergies with national initiatives | 3 | 2 | 6
WP3 | T3.4 - Monitoring of national support | Provide timely feedabck and monitoring reports | 1 | 1 | 1
WP5 | T5.1.1 - Database of investors and relevant stakeholders | Build an extensive live database of (national / regional) potential investors suitable for EUCF investment concepts. | 1 | 9 | 9
WP5 | TF5.1.3 - IC matchaking activities with investors | Support the LIFE EUCF Team in the organisation of roadshows. Support the LIFE EUCF Team in the organisation of national matchmaking events | 1 | 15 | 15
WP5 | TF5.3 Pilot schemes | Carry out pilot study to assess the feasibility of replicating the EUCf model at national / regional level. | 1 | 50 | 50
93